## Sheet1
TASK | TASK | TASK | PROGRAMMING | START | DUE | DURATION | PCT OF TASK | WEEK 1 - Beginning 17/02/2025 |  |  |  |  | WEEK 2 - Beginning 24/02/2025 |  |  |  |  | WEEK 3 - - Beginning 03/03/2025
ID | TITLE | OWNER | LANGUAGES | DATE | DATE | IN DAYS | COMPLETE | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
1 | Project Setup & Infrastructure
1.1 | Set Up Flask Project Structure | Yahya | Py, terminal | 2025-02-18 | 2025-02-21 | 3 | 100%
1.2 | Set Up Database (CSV Import) | Adam | SQL | 2025-02-18 | 2025-02-21 | 3 | 100%
1.3 | Develop Main Application Foundation (app.py) | Yahya | Python | 2025-02-18 | 2025-02-21 | 3 | 100%
2 | User Authentication & Management
2.1 | Create Login Page (login.html) | Yahya | HTML,JS,Py | 2025-02-20 | 2025-02-25 | 5 | 100%
2.2 | Design Signup Page (signup.html) | Yahya | HTML,JS,Py | 2025-02-20 | 2025-02-25 | 5 | 100%
2.3 | Implement User Login System | Yahya | HTML,JS,Py | 2025-02-20 | 2025-02-25 | 5 | 90%
2.4 | Develop Login & Logout Functionality
2.5 | Set Up Password Reset Functionality | [5 empty] | 0%
2.6 | Build User Profile Page (profile.html) | [5 empty] | 0%
2.7 | Design User Profile Management Page | [5 empty] | 0%
3 | Admin Features
3.1 | Create Admin Dashboard (admin-dashboard.html) | Barirah | HTML,JS,Py | 2025-02-25 | 2025-03-04 | 7 | 100%
3.2 | Manage Admin Session & Privileges | Barirah | HTML,JS,Py | 2025-02-25 | 2025-03-04 | 7 | 60%
4 | Core Application Pages
4.1 | Develop Homepage (home.html) | Aadam | HTML,JS,Py | 2025-02-20 | 2025-02-25 | 5 | 100%
4.2 | Filter Data | Harris | HTML,JS,Py | 2025-02-20 | 25/02/2025 | 5 | 60%
4.3 | Implement Historical Data Page (historical-data.html) | Harris | HTML,JS,Py | 2025-02-20 | 2025-02-25 | 5 | 100%
4.4 | Develop Sensor Data Page (sensordata.html) | Osman, Saif | HTML,JS,Py | 2025-02-25 | 2025-03-04 | 7 | 70%
5 | Data Management & Visualization
5.1 | Enable CSV & Excel Data Export | Osman, Saif |  |  |  |  | 0%
5.2 | Integrate Line & Bar Graph Visualizations | Osman, Saif | HTML,JS | 2025-02-25 | 2025-03-04 | 7 | 100%
5.3 | Develop Live Data Simulation (30s Interval) | Aadam | Javascript | 2025-02-20 | 2025-02-25 | 5 | 100%
6 | Traffic Light System
6.1 | Produce Machine Learning Method | Ramzan, Saif | Python | 2025-02-25 | 2025-03-04 | 7 | 50%
6.3 | Produce Temp Traffic Light System | Ramzan | Javascript | 2025-02-25 | 2025-03-05 | 8 | 80%
6.4 | Integrate Machine Learning Method | Ramzan | Py,JS | 2025-02-25 | 2025-03-05 | 8 | 0%
7 | Documentation & User Support
7.1 | Create Help Page (help.html) | Harris | HTML,CSS | 2025-02-25 | 2025-03-04 | 7 | 100%
7.2 | Create FAQ Page with Categorized Sections | Harris | HTML,CSS | 2025-02-25 | 2025-03-04 | 7 | 100%
7.3 | Implement User Guide Pages | Harris | HTML,CSS | 2025-02-25 | 2025-03-04 | 7 | 0%
8 | Responsive Design
8.1 | Ensure Mobile & Tablet Responsiveness |  | HTML,CSS |  |  |  | 50%